DDA PLATFORM

24-Hour Hackathon War Plan

4 Engineers  ·  4 MVPs  ·  5 Phases  ·  Zero Fluff

| You (Backend Lead) Auth · AI Service · Alerts · Team Lead | Backend Engineer 2 DB · CRUD APIs · WebSocket · Analytics | Frontend Engineer 1 Dashboard · Live Map · KPI Cards · Alerts UI | Frontend Engineer 2 Field Form · AI Results · List View · Demo |
| --- | --- | --- | --- |

# ⚡ Most Important Moment: Hour 4 Handoff

At Hour 4, YOU must share the API contracts doc with both Frontend Engineers. This is the single most critical moment of the hackathon. If this slips, both FE tracks stall. Include endpoint URLs, request/response JSON shapes, and auth headers. A simple Notion page or markdown file is enough.

# Phase-by-Phase Task Breakdown

Phase 0: Setup & Foundation Hour 0–2

| Assigned To | Task | Priority |
| --- | --- | --- |
| You (Backend Lead) | Scaffold monorepo, Docker Compose (Postgres, Redis, Kafka), shared .env, GitHub repo + branches | 🔴 CRITICAL |
| Backend Engineer 2 | DB schema design + migrations (assessments, users, alerts tables), seed demo data script | 🔴 CRITICAL |
| Frontend Engineer 1 | Next.js 14 project init, Tailwind + Shadcn setup, Leaflet.js install, auth page skeleton | 🟢 Standard |
| Frontend Engineer 2 | React assessment form project init, React Query setup, form component architecture plan | 🟢 Standard |

Phase 1: Core APIs + Auth Hour 2–7

| Assigned To | Task | Priority |
| --- | --- | --- |
| You (Backend Lead) | Auth service: JWT login/register, RBAC middleware (Admin / Supervisor / Assessor roles), protect all routes | 🔴 CRITICAL |
| You (Backend Lead) | Define & document API contracts (OpenAPI spec) for ALL endpoints — share with FE team by Hour 4 ⚡ | 🔴 CRITICAL |
| Backend Engineer 2 | Assessment CRUD API: POST /assessments, GET /assessments, GET /assessments/:id, PATCH /assessments/:id/verify | 🔴 CRITICAL |
| Backend Engineer 2 | File upload service: photo upload to MinIO/local, return URL, link to assessment record | 🔴 CRITICAL |
| Frontend Engineer 1 | Dashboard layout: sidebar nav, header, responsive grid. Auth flow (login → dashboard redirect) | 🟢 Standard |
| Frontend Engineer 2 | Assessment form: all fields (location, damage type, severity, photos), validation, submit to API | 🔴 CRITICAL |

Phase 2: AI + Map Layer Hour 7–14

| Assigned To | Task | Priority |
| --- | --- | --- |
| You (Backend Lead) | AI service: integrate pre-trained ResNet50 (xBD dataset), POST /ai/classify endpoint — returns damage class + confidence | 🔴 CRITICAL |
| You (Backend Lead) | Severity scoring algorithm: weighted formula (structure 30% + damage 35% + persons 20% + infra 15%) → score 0–100 | 🔴 CRITICAL |
| Backend Engineer 2 | Geospatial queries: GET /map/heatmap returns GeoJSON with severity + coordinates for all assessments | 🔴 CRITICAL |
| Backend Engineer 2 | WebSocket server (Socket.io): emit newAssessment event on every POST, broadcast map updates to dashboard clients | 🔴 CRITICAL |
| Frontend Engineer 1 | Live damage map: Leaflet heatmap layer from /map/heatmap, cluster markers, real-time update via WebSocket | 🔴 CRITICAL |
| Frontend Engineer 2 | Connect form to AI: show live damage classification result + auto-fill severity score after photo upload | 🔴 CRITICAL |

Phase 3: Alerts + Dashboard KPIs Hour 14–19

| Assigned To | Task | Priority |
| --- | --- | --- |
| You (Backend Lead) | Alert rules engine: check severity thresholds on every AssessmentCreated event, fire alert if score > 70 | 🔴 CRITICAL |
| You (Backend Lead) | Notification dispatch: in-app alert + log to DB (show in UI — no SMTP needed for demo) | 🔴 CRITICAL |
| Backend Engineer 2 | Analytics API: GET /analytics/summary → total assessed, severity breakdown, top 5 critical zones, structures by type | 🔴 CRITICAL |
| Backend Engineer 2 | Report PDF generator: pdfkit/puppeteer to auto-generate assessment summary, GET /reports/generate | 🟢 Standard |
| Frontend Engineer 1 | KPI cards: total assessments, critical zones, people affected, coverage %. Pull from /analytics/summary | 🔴 CRITICAL |
| Frontend Engineer 1 | Alerts panel: real-time notification bell + side drawer showing all fired alerts with severity badge + zone info | 🔴 CRITICAL |
| Frontend Engineer 2 | Assessment list view: filterable table (by severity/zone/date), status badges, click-to-view detail modal | 🟢 Standard |

Phase 4: Polish + Demo Prep Hour 19–24

| Assigned To | Task | Priority |
| --- | --- | --- |
| You (Backend Lead) | TEAM LEAD: Integration testing all flows end-to-end. Fix any blocker bugs. Final Docker Compose up --build check | 🔴 CRITICAL |
| You (Backend Lead) | Seed realistic demo data: 3 disaster zones, 20 assessments across severity levels, 5 fired alerts | 🔴 CRITICAL |
| Backend Engineer 2 | Performance: add Redis caching on /analytics/summary + /map/heatmap. Add basic rate limiting on POST routes | 🟢 Standard |
| Frontend Engineer 1 | Dashboard polish: loading skeletons, error states, empty states, smooth map animations, mobile responsive | 🟢 Standard |
| Frontend Engineer 2 | Form UX polish: GPS auto-detect, photo preview grid, offline banner, success toast on submit | 🟢 Standard |
| Frontend Engineer 2 | Prepare 3-min demo: login → submit assessment → watch map update → alert fires → dashboard KPIs | 🔴 CRITICAL |

# ⏱️ Critical Path Checkpoints

These are the 8 checkpoints that define success. If any of these slip by more than 30 minutes, reprioritize immediately.

| Checkpoint | What Must Be True |
| --- | --- |
| Hour 0–2 | Docker Compose running, DB schema finalized, both FE projects initialized |
| Hour 4 ⚡ | API contracts shared with FE team — CRITICAL HANDOFF — unblocks both FEs |
| Hour 7 | Auth + Assessment CRUD working, FE starts hitting real APIs |
| Hour 10 | AI classify endpoint live, map GeoJSON endpoint live |
| Hour 14 | WebSocket live updates working end-to-end |
| Hour 19 | All 4 MVP features functional — switch to polish only |
| Hour 22 | Demo data seeded, full flow rehearsed once |
| Hour 24 | SUBMIT 🚀 |

# ⚠️ Risk Register & Mitigations

Pre-planned mitigations for the 5 most likely failure points in a 24-hour sprint.

| Risk | Mitigation Plan |
| --- | --- |
| AI model too slow / inaccurate | Pre-download ResNet50 weights before hackathon starts. Fallback: rule-based scoring only (still counts as AI layer for judges) |
| WebSocket real-time fails | Fallback: 10-second polling on dashboard. Same demo UX, much simpler code |
| FE blocked waiting for APIs | Hour 4 API contract doc + mock JSON responses so both FE engineers can build independently |
| Scope creep | Offline sync, PDF reports, multi-language — all CUT. Focus exclusively on the 4 MVPs |
| Integration hell at Hour 19+ | 15-min team syncs at Hour 7 and Hour 14 — surface blockers early, don't let them fester |

# 📅 Team Sync Schedule

| Time | Duration | Agenda |
| --- | --- | --- |
| Hour 0 | 30 min | Kickoff — divide tasks, set up communication channel, confirm dev environments working |
| Hour 4 ⚡ | 20 min | API contracts handoff — You share endpoint specs with both FE engineers. Blocker check. |
| Hour 7 | 15 min | Mid-point sync — is auth + CRUD working? FE on track? Surface any blockers. |
| Hour 14 | 15 min | AI + WebSocket check — are real-time updates flowing? Map rendering correctly? |
| Hour 19 | 20 min | Feature freeze check — all 4 MVPs working? Switch to polish + demo prep mode. |
| Hour 22 | 30 min | Demo rehearsal — full flow once. Identify last-minute fixes needed. |

DDA Platform  ·  24-Hour Hackathon War Plan  ·  Team Confidential

4 Engineers  ·  Field Assessment  ·  Live Map  ·  AI Classification  ·  Alerts